| Phase | Dates | Process Step | Resources Needed from Client Name | Your Business Name Deliverables |
| --- | --- | --- | --- | --- |
| I | 12/05/18 to 12/19/18 (2 weeks) | Compensation Philosophy, Market Pricing Guidelines | - Obtain organizational charts - Discuss and decide with client compensation philosophy and market pricing guidelines - Obtain a Job Title listing for all jobs will be benchmarking - Forward job descriptions to Your Business Name via email by xx/xx - Availability and preparation for call and/or answers to email to complete market data guidelines | - Project plan - Conference call to establish compensation philosophy and market pricing guidelines - Documentation of compensation philosophy and market pricing guidelines following call |
| II | 12/20/18 to 01/25/19 (5 weeks) | Initial Market Matches | - Availability to answer questions on positions - Availability for meeting | - Initial market matches for xxx positions pulled and sent for review - Meeting or phone call to review initial market matches |
| III | 01/28/19 to 02/08/19 (2 Weeks) | Market Pricing – Final Pass | - Availability for conference call | - Conference call to review any changes that were made to market matches - Final excel spreadsheet of consolidated market data |
| IV | 02/11/19 to 02/28/19 (3 weeks) | Create Salary Structure | - Availability for conference call | - Initial Salary Structure(s) - All jobs slotted into structure that were benchmarked - Call to review salary structure |
| V | 03/04/19 to 03/22/19 (3 Weeks) | Incumbent Analysis | - Employee census data | - Complete incumbent analysis - Call to review incumbent analysis |
| VI | 03/25/19 to 04/12/19 (3 weeks) | Final Presentation | - Availability for meeting | - Wrap-up any outstanding items - Develop final presentation - Meeting to review final presentation on new base pay structure |