## Sheet1
BASE PAY PROJECTS PROPOSAL TEMPLATE
Prospect | Sample Client
Date | xx/xx/xx
# Jobs | 30
# Employees | 155
|  | Team Member #1 | Team Member #2 | Notes
Step 1 Project Planning
| Initial Meeting | 1
| Write Proposal | 1
Step 2 Strategy & Philosophy
| Project Plan | 1
| Resources from Client |  | 1
| Comp Phil/Mkt Data Guidelines |  | 1
| Initial Meeting | 1
Step 3 Market Pricing
Gather JD's/JCQ's
| Create job title listing |  | 2
| Pull matches and data |  | 30
Additional Surveys
Complex Scopes
| Meeting to review matches |  | 5
| Changes to market matches |  | 3
| Review changes with client |  | 2
Cursory FLSA Review
Step 4 Salary Structure
| Draft salary structure |  | 4
| Meeting to review structure | 1
| Make changes to structure |  | 1
| Finalize structure |  | 1
| Additional structures/geo differentials |  | 2 | 6 cities
| Slot jobs |  | 1
| Meet with client on final structure and slotting |  | 1
Step 5 Job Families
Create job families/slot jobs
Draft levels and descriptors
Meeting with client to review
Revisions to job families
Step 6 Analysis
| Incumbent Analysis |  | 4
Discrimination Analysis
| Pay Mix Analysis |  | 1
| Meeting with client | 1
Step 7 Ala Carte Items
Managers Compensation Guide
Develop Training
Deliver Training
Create Job Descriptions
In-depth FLSA Review
Step 8 Reports and Presentation
| Create report/presentation |  | 3
| Deliver report/presentation | 2
Hours Sub-Total |  | 8 | 62
Sub-Total Fees |  | 13650
Admin Fee - 10% of all Sub-Totals |  | 1365
Referral Fee | Pay to: N/A | 0
TOTAL PROJECT FEE |  | 15015